## Sheet1
Monthly Review for Engineer Trainees
Name of Trainee | Prachi Gulihar |  |  |  |  | Supervisor : Tarun Gupta
Emp_Id | 3122 |  |  |  |  | Month-Year : April- 2019
(Rate on a scale of 1-5, 1 being lowest & 5 being highest)
Task Assigned | Target Date | Completion Date | Quality of Work | Self Rating | Supervisor's Rating | Review Remarks
Golden AMI | 2019-04-05 | 2019-04-05 | The task was to set up golden AMI golden AMI vulnerability assessments setup process was explored using cloud formation and there were invalid principal policy errors. | 5
Golden AMI integrated with Qualsys | 2019-04-08 | 2019-04-08 | Qualsys is a third party which provides vulnerability assessment scanning tools for aws services and a trial assessment can be done free of cost. | 5
AMI hardening Ubuntu EC2 instance | 2019-04-12 | 2019-04-12 | Ubuntu instance was exposed to a vulnerability and then assessment was done to verify whether the exposed vulnerability is identified correctly. | 5
Amazon Inspector assessment run on egsp-uat instance | 2019-04-15 | 2019-04-15 | Egsp-uat instance was set as target for the assessment and the process was halted because of unavailability of the inspector agent. | 5
Assessment run on Eventifyd Instance | 2019-04-19 | 2019-04-19 | The assessment run target was reset to Eventifyd ec2 instance which is ubuntu machine with tomcat server and phpmyadmin to host mind contact us service page. | 5
Linux AMI Patching of the Eventifyd Instance | 2019-04-22 | 2019-04-22 | Aroud 248 vulnerabilities were identified by the run and patching was done according to the priorities identified with the help of quality assurance team | 5
Agent Unknown Network Connectivity Setup | 2019-04-17 | 2019-04-17 | Agent unknnown status was shared with amazon support team and after initial troubleshooting steps the agent logs of the machine were shared with the networking team. | 5
Session on emerging trends in technology | 2019-04-24 | 2019-04-24 | Various upcoming technologies and their future scope was discussed which included blockchain, cloud, IOT, voice. | 5
Alexa online conference for voice developers | 2019-05-01 | 2019-05-01 | Online conference was conducted in which blueprints, multimodal skills and gaming in voice was discussed by the evangelists. | 5
Understanding kibana graph generation working | 2019-04-29 | 2019-04-29 | I understood how the visualization of various aws logs was done through Kibana, better graph metrics are to be worked on for useful inferences like cost optimization through billing graphs. | 5
Lambda for automating the remediation | 2019-05-02 | 2019-05-02 | On identifying new vulnerabbilities on the next assessment a notification is sent over the email by SNS and the lambda updates the OS to the latest patched version. | 5
OCR Engine use case | 2019-05-04 | 2019-05-04 | The dot-matrix text is to be extracted from the image captured, this is currently using google vision API but the costing is around five laks per month so alternative approch needs to be built. | 5
Behavioral Skill |  |  | Rating | Remarks / Scope for Improvement
Learning Attitude |  |  | 5 | Keen on learning how things work and new methods to accomplish a task
Discipline / Attendance |  |  | 5 | Following the code of conduct and maintaining punctuality
Flexibility / Approach |  |  | 5 | Flexible and adaptive to different kinds of tasks being assigned
Rating by Supervisor | (Poor/Average/Good/Very Good /Excellent)
Name of Supervisor | Tarun Gupta
Project Name
Signature with Date