## Sheet1
Monthly Review for Engineer Trainees
Name of Trainee | Prachi Gulihar |  |  |  |  | Supervisor : Tarun Gupta
Emp_Id | 3122 |  |  |  |  | Month-Year : January- 2019
(Rate on a scale of 1-5, 1 being lowest & 5 being highest)
Task Assigned | Target Date | Completion Date | Quality of Work | Self Rating | Supervisor's Rating | Review Remarks
Json parsers for gstr3b | 2019-01-07 | 2019-01-07 | The nested json file was to be mde flat for four kinds of bussiness types of EGSP. | 5
Alexa STARS token discussion | 2019-01-09 | 2019-01-09 | The user identification problem of integrating STARS app with Alexa was discussed as the token was getting expired. | 5
AWS Alexa skill development Beta exam | 2019-01-14 | 2019-01-14 | Attempted AWS alexa skill development exam it was a mix of questions, was able to solve the questions pertaining to interaction model and lambda errors. | 4
Setup Eclispse AWS Toolkit on RDP Machine | 2019-01-18 | 2019-01-18 | The proxy network setting was not allowing to setup AWS toolkit on local machine so the lambda code had to shifted to EC2 instance. | 5
Unzip the json data being uploaded in s3 | 2019-02-19 | 2019-02-19 | Instead of json files a buch of files was being inuted and ZIpInputStream API was not supported by lambda so file format was changed. | 5
Dyanmic S3 path creation | 2019-02-20 | 2019-02-20 | The key of the file triggering the lambda fuction was extracted and the same key was used to put data in the final S3 bucket. | 5
Populating flat jason data to Athena | 2019-01-25 | 2019-01-25 | The Athena tables were to be altered as new flat json files were being created. | 5
Querying the Athena flat json data | 2019-02-28 | 2019-02-28 | The new data pushed into Athena tables was checked for correct partitioning and correct values. | 5
Updating the flag values of Postgres columns | 2019-02-01 | 2019-02-01 | File successfully uploaded flags had to be set and reflected in UI after the flat files were put in ATHENA tables. | 5
End to End Lambda Testing | 2019-02-04 | 2019-02-04 | The whole flow of pipeline from input data to summary creation undergone integration testing after unit testing was complete. | 5
Behavioral Skill |  |  | Rating | Remarks / Scope for Improvement
Learning Attitude |  |  | 5 | Keen on learning how things work and new methods to accomplish a task
Discipline / Attendance |  |  | 5 | Following the code of conduct and maintaining punctuality
Flexibility / Approach |  |  | 5 | Flexible and adaptive to different kinds of tasks being assigned
Rating by Supervisor | (Poor/Average/Good/Very Good /Excellent)
Improvement Area / Special Comments (Mandatory field to be filled by supervisor)
Name of Supervisor | Tarun Gupta
Project Name
Signature with Date