## Sheet1
S.No. | Activity | Target Completion Dates | Revised Target Completion Dates | Actual Completion Dates | Current Status ( Completed / In-Progress / Not-Started)
1 | ICAI- Design Document Version 1 | 2021-12-01 |  | 2021-12-01 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Others\
2 | ICAI- Design Document Version 2 | 2021-12-01 |  | 2021-12-01 | Completed | Same as above
3 | Kenda- Blog | 2021-12-02 |  | 2021-12-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
4 | Kendra- Learning Doc | 2021-12-10 |  | 2021-12-10 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
5 | Sagemaker Blog | 2021-07-22 |  | 2021-07-22 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\Sagemaker
6 | Sagemaker Document | 2021-07-21 |  | 2021-07-21 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\Sagemaker
7 | Sagemaker custom model - Learning document | 2021-12-02 |  | 2021-12-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\Sagemaker
8 | Sagmaker custom Model - Implement + Document the learnings for below custom model deployment Immersion day training on custom model deployments https://sagemaker-immersionday.workshop.aws/lab3.html | 2021-12-03 |  | 2021-12-03 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
9 | Redshift Learning Document | 2021-09-03 |  | 2021-09-03 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
10 | Redshift- Blog | 2021-12-06 |  | 2021-12-07 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
11 | Rekognition+Lex Blog | 2021-07-15 |  | 2021-07-15 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
12 | Rekognition+Lex- Learning Doc | 2021-12-06 |  | 2021-12-06 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
13 | Session on EMR / Glue from - Shailja / Umesh | 2021-12-07 |  | 2021-12-07 | Completed
14 | EMR+Glue- Learning Doc | 2021-12-07 |  | 2021-12-08 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
15 | EMR+Glue- Blog | 2021-12-08 | 2021-12-09 | 2021-12-09 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
16 | ElasticSearch- Learning Doc | 2021-12-09 | 2021-12-10 | 2021-12-10 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
17 | ElasticSearch- Blog | 2021-12-09 | 2021-12-10 | 2021-12-10 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
18 | Blog - Quicksight | 2021-07-26 | 2021-07-26 |  | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
19 | Quicksight- Learning Doc | 2021-12-10 | 2021-12-13 | 2021-12-13 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
20 | Comparison- Athena, Presto, Hive, SparkSql | 2021-12-13 | 2021-12-14 | 2021-12-15 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Other
High level review & correction
| Case Study - Maruti EMR | 2021-12-14 |  | 2021-12-14 | Completed | Old work folder
| Case Study - Convosight - Redshift / Glue | 2021-12-14 |  | 2021-12-14 | Completed | Same as above
| Case Study - Day-to-Day - Redshift ( Bishan / Abhishek) | 2021-12-15 |  | 2021-12-17 | Completed | Same as above
| Case Study - ICAI kendra | 2021-12-16 |  | 2021-12-16 | Completed | Same as above
| Case Study - Elastic Search ( Rishi Airy)-seek from Shailja | 2021-12-16 | 2021-12-21 | 2021-12-28 | Completed | Same as above
| AWS+Google+Azure cloud DA+ML services compilation | 2021-12-20 |  | 2021-12-20 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Other
| GUS- Glue usage focus case study | 2021-12-21 |  | 2021-12-21 | Completed
| Compile current write-ups in network drive location | 2021-12-21 |  | 2021-12-21 | Completed
Checklist filling
| Redshift Checklist filling for 2 customers |  |  | 2022-01-07 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\SA sheets
| DA self assessment sheet filling | 2022-01-17 |  | 2022-01-18 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\SA sheets
Deep technical blogs(we will work together)
| Rekognition – SmartHealth | 2022-01-28 | 2022-01-31 | 2022-02-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
| Custom Sagemaker model | 2022-01-24 | 2022-02-02 | 2022-03-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\Sagemaker
| Credit scoring model | 2022-04-02 | 2022-07-02 | 2022-07-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
| ML Training - New Services ( Monitron, Panaroma, DeepComposer , HealthLake, DevOPS Guru etc) | 2022-02-20 | 2022-08-08 | 2022-09-03 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Others\Comparisons
| ML Ops | 2022-02-22 | 2022-07-03 | 2022-08-03 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\Sagemaker
Presentations
| Credit Scoring Model (Source Data – Pipeline - Serving) | 2022-10-02 |  | 2022-11-02 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Other
| For Kendra ( as additional) | 2022-10-02 |  | 2022-11-02 | Completed | Same as above
| Rekognition for Quality inspection | 2022-11-02 |  | 2022-11-02 | Completed | Same as above
| Accelerated Document Processing (Textract) | 2022-11-02 |  | 14/2/2022 | Completed | Same as above
| Demand Forecasting using AWS Forecast | 2022-11-02 |  | 14/2/2022 | Completed | Same as above
| Data Warehouse ( Convosight) | 14/2/2022 |  | 14/2/2022 | Completed | Same as above
| Data Lake ( Samrx example, Allcloud) | 14/2/2022 |  | 15/2/2022 | Completed | Same as above
| Fraud Detection | 2/18-2/21 |  | 2/18-2/21 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
| Custom Sagemaker model demo | 2022-09-02 | 2022-11-02 | 25/2/2022 | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Immersion day
| Slides using existing slides | 2022-02-07 | 2022-09-03 | 2022-10-03 | Completed
| Sample code | 2022-02-09 | 2022-09-03 | 2022-11-03 | Completed
| ML workload migration assessment | 29/3/2022 | 29/3/2022 |  | Completed | SA sheet folder
| Kafka document | 31/3/2022 | 31/3/2022 |  | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\Services\
| Video recording session- custom model notebook | 2022-08-04 | 2022-08-04 |  | Completed | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT

## Sheet2
KT | Resource | Status
Documentation | Atul | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
ICAI Kendra | Rohit | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Account Creation | Nishul | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Sagemaker Custom Model | Atul | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Alexa | Rohit | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Chatbot | Rohit | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT
Sumerian | Manish | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT | mail
Maruti sheet | Umesh sir | Done | Z:\AI-ML Team Working\Prachi Gulihar\New Work\KT | mail